## LOG requests
LOG REQUESTS
Date | Time | Request Made By | RE Practice/ Pharmacy | Description | Sent to | Result | Closed Date
2016-11-14 | 7:34 | Bill E | Kaikoura | no power. | SITREP |  | 15/11, 13:45
2016-11-14 | 7:34 | Bill E | Kaikoura | no sewer. | SITREP | Portaloos on ship 16/11? | 16/11.
2016-11-14 | 7:34 | Bill E | Hanmer | no power. | SITREP |  | 15/11.
2016-11-14 | 7:54 | Bill E | Amuri | no power. |  | Power back on. | 14/11, 11:56
2016-11-14 | 7:54 | Bill E | Amuri | Amuri GP stuck in Hanmer. |  |  | 14/11.
2016-11-14 | 10:15 | Bill E | Cheviot | no power. |  | Generator supplied by St John. | 14/11, 10:56
2016-11-14 | 10:56 | Bill E | All | questions re building engineer's checks - are they required? | Phil
2016-11-14 | 13:10 | Bill E | Darfield | no telephone (cable cut by contractors) |  |  | 14/11, 16:43
2016-11-14 | 16:43 | Bill E | Cheviot | locum cover arranged for Tues-Fri |  | Locum GP arrived | 15/11, 9:58
2016-11-14 | 16:43 | Bill E | Woodend CD Ctr | mental health team on site |  |  | 14/11.
2016-11-14 | 17:04 | Gareth | Kaikoura Pharmacy | operating a rudimentary dispensing service out of hospital. | SITREP |  | 15/11.
2016-11-15 | 9:58 | Bill E | Waimak | increase pt stress and anxiety. Need extended mh consult funding. |  | RCPHO sending BICs.
2016-11-15 | 10:00 | Bill E | Amuri | no radio |  | Repeater station fixed. | 14/11, 10:02
Sample Logistics record. All calls and emails can be entered into this spreadsheet with resulting actions noted.

## distrib
SITREP Distribution:
Philip Schroeder - Rolleston Central Health <philip.schroeder@rollestonhealth.co.nz>; Graeme McColl (ilsogno@snap.net.nz); Kelly & Don <keldon47@xtra.co.nz>; Gareth Frew <gareth.frew@ccpg.org.nz>; Jock Muir (jock.muir@cdhb.health.nz); Mary Gordon (Mary.Gordon@cdhb.health.nz) (Mary.Gordon@cdhb.health.nz); Carol Glover (Carol.Glover@pegasus.org.nz); Bill Eschenbach <bill_eschenbach@rcpho.org.nz>; Geraldine Clemens (Geraldine_Clemens@rcpho.org.nz); Vince Barry <Vince.Barry@pegasus.org.nz>; Laila Cooper (laila.cooper@chchpho.org.nz); jenny.ewing@cdhb.health.nz; Mark Liddle <Mark.Liddle@pegasus.org.nz>; Lisa Brennan <Lisa.Brennan@pegasus.org.nz>; Kim Burgess <Kim.Burgess@pegasus.org.nz>; ECC Operations (ECC.Operations@cdhb.health.nz); pugowner@xtra.co.nz; carolyn.gullery@cdhb.health.nz
Distribution List for SITREPs may differ between events. Need to understand early on who wants information from primary care.
Also need to add CPRG Forum members.

## contacts
Contacts
For | Who | Role | Phone | Email
Kaikoura | Andrea Judd | GP, main contact | 027 686 3636 | andreaj@kaikourahc.co.nz
Kaikoura | Anu Shimmeron | Rural Hospital Trainee Registrar
Kaikoura | John Simpson | nights
Kaikoura | Gayle | Nursing Coord for Inpatients
Kaikoura | Helen Percy | Nursing Coord for gen'l practice | 021 810 715
Kaikoura | Wendy Campbell | Practice Manager | 03 319 3500 | admin@kaikourahc.co.nz
CDHB | Win McDonald | Transition Programme Manager | 027 224 1638
CDHB | Jacinda King | travel
Pegasus | Simon Brokenshire | 24HS Clinical Director - for Kaik GP/PN locum | 021 242 9734 | simon.brokenshire@pegasus.org.nz
Pegasus | Carol Glover | Rural Health Manager (handling Kaikoura) | 021 405 788 | carol.glover@pegasus.org.nz | pugowner@xtra.co.nz
CPRG | Deborah Callahan | Primary Care EOC | 021 414 796 | incident@pegasus.org.nz | 03 353 9966
CDHB | Becky Hickmott | Clinical queries via Duty Managers of each Hospital | 027 212 7279
CDHB | Chris Dever | Public Health – HPO On Call as first contact | 027 449 7589 | chris.dever@cdhb.health.nz
CDHB | David Collins | CDHB Emergency Coordinator | 027 538 3865 | david.collins@cdhb.health.nz
CDHB | David Meates |  | 0274 924 505 | david.meates@cdhb.health.nz
CDHB | Jenny Ewing | Emergency Planning Manager | 0088 1621 433904 (based in Kaikoura) | jenny.ewing@cdhb.health.nz
CDHB | Jacinda King | Staffing | 027 383 5744 | jacinda.king@cdhb.health.nz
CDHB | Janice Lavelle | CD Liaison | 027 434 1699 | janice.lavelle@cdhb.health.nz
CDHB | Jock Muir | 1st contact Logistics | 027 479 1188 | jock.muir@cdhb.health.nz
CDHB | John Osborne | CDHB Supply Logistics | 027 382 6598 | john.osborne@cdhb.health.nz
CDHB | Karalyn van Deursen | CDHB Strategic Comms | 027 531 4796 | karalyn.vandeursen@cdhb.health.nz
CDHB | Kate Gibb |  | 021 766 766 | kate.gibb@cdhb.health.nz
CDHB | Mark Newsome |  | 027 245 9595
CDHB | Mary Gordon | CDHB Incident Controller | 027 477 7361 | mary.gordon@cdhb.health.nz
CDHB | Megan Gibbs | CD Liaison | 027 212 7361 | megan.gibbs@cdhb.health.nz
CDHB | Michael Flatman | Backup Logistics | 021 421 531
CDHB | Mick O’Donnell | CDHB Comms | 027 261 4824 | mick.odonnell@cdhb.health.nz
CDHB | Rachel Cadle | Food | 027 212 7310 | rachel.cadle@cdhb.health.nz
CDHB | Sarah Gibbon | Staffing | 027 354 5830 | sarah.gibbon@cdhb.health.nz
CDHB | Stella Ward | Vulnerable People | 027 593 2453 | stella.ward@cdhb.health.nz
CDHB | Toni Gutschlag | Vulnerable People | 027 212 7305 | toni.gutschlag@cdhb.health.nz
CDHB | Warren Holm | CD Liaison | 027 652 7264
CDHB | Win McDonald | CDHB Kaikoura Hospital Liaison | 027 224 1638 | win.mcdonald@cdhb.health.nz
CPRG | Phil Schroeder | Primary Care | 021 347 224
CPRG | Graeme McColl | Primary Care | 027 329 4227
MOH | Murray Halbert | MOH Liaison | 021 829 502
Civil Def | Neville Reilly | CD Controller | 027 270 2762
NZ Rural GP Network | Linda Reynolds | Deputy Chief Executive | 021 547 161 | linda@rgpn.org.nz
Amberley MC | Penny Forde | Receptionist | 03 314 8504 | penny@amberleymc.co.nz
Amberley MC | Nicki Greenwood | district nurse | 027 635 9295
Oxford | Chantal Woodham | Practice Manager | 021 407 440 | chantal@ochc.co.nz
Amberley MC | Denise Cope | Practice Manager | 027 200 5228 | denise@amberleymc.co.nz
Unichem Spitfire | David | Pharmacist
Hanmer Health | David Smith | Practice Manager | 027 4311 212 | manager@hanmermc.co.nz
Public Health Nursing | Kate Parfitt | Public Health Nurse | 027 221 1223 | kate.parfitt@cdhb.health.nz
Public Health Nursing | Vicky Brewer | Charge Nurse Manager | 027 480 8494 | vicky.brewer@cdhb.health.nz
Akaroa | Howard Wilson | GP | 027 407 9559
Amuri | Anne Sheard | DN coordinator at Amuri
Amberley MC | Liz Thomas | DN at Amberley
Public Health Nursing | Linda Craig | PHN | 027 433 6531
Tuahiwi | marae
Rehua | marae
Nga Hau e Wha | marae
Community & Public Health | Daniel Williams | Public Health Physician | 027 230 9303 | daniel.williams@cdhb.health.nz
Plunket | Linda Hill | Pregnancy & Parenting Manager | 021 514 679 | linda.hill@plunket.org.nz
CDHB P&F | Deb Parker | PA to Carolyn Gullery | 364 4160 | deb.parker@cdhb.health.nz
Midwives | Alison Eddy | NZCOM - College of Midwives |  | alison.e@nzcom.org.nz
LMC Kaikoura | Bernie
Kaikoura BIC | Lynda Kitchingham | RCPHO | 027 486 6321 | ochiltree@xtra.co.nz
Contacts may differ between events.
ECC@cdhb.health.nz needs to be confirmed early on as the Single-Point-of-Entry for the health response.

## roster
Personnel Roster
Name | Role | Cell |  | Email/other info | In/Out | Out | Contract Sent | Contract Rec'd | Timesheet/Invoice Rec'd | Processed | Invoiced to CDHB | Notes
Doctor A | GP |  | Cheviot |  | in 22/11 - out 22/11 | 1
Doctor B | PN |  | Kaikoura |  | in 29/11 - out 1/12 from Cheviot
Sample - Separate Excel spreadsheet may also be used.

## all status
2016-12-12 | 2016-12-08 | 2016-12-05 | 2016-12-02 | 2016-12-01 | 2016-11-30 | 2016-11-29 | 2016-11-28 | 26-27 Nov | 2016-11-25 | 2016-11-24 | 2016-11-23 | 2016-11-22 | 2016-11-21 | 19-20 Nov | 18/11 Status | 17/11 Status | 16/11 Status | 15/11 Status
0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 4
2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 10 | 4 | 2 | 2 | 6 | 6 | 6
4 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 10 | 4 | 2 | 2 | 6 | 8 | 8
2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 6 | 8
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 4 | 2 | 4 | 4 | 4 | 4
2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 8
10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 8 |  | 12
10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 16 | 16 | 14 | 16 | 16 | 14 | 14
0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 2
This could be useful for Primary Care Coordinators, CDHB ECC, etc. to track practice and pharmacy status over time

## 17 Nov
LEG | Type | Surgery/Pharmacy | Address | Business Phone | Emergency Contacts | Role | Cellphone | Homephone | Email1 | Email2 | STATUS | Building | Services | Staff | Income | 16/11 Status | 15/11 Status | 2016-11-17 | 2016-11-16 | LOGISTIC NEEDS
Rural 2 | Surgery | Amberley Medical Centre | 6 Hilton Drive Amberley | 03 314 8504 | Long, Christine | Nurse | 0274278813 | 03 314 9077 | chrisl@amberleymc.co.nz | long.chris@xtra.co.nz | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 17/11. No additional information. | 16/11. Fully operational.
Rural 2 | Pharmacy | Amberley Pharmacy | 127a Carters Rd Amberley | 03 314 8211 | Watt, Paul | Pharmacist | 0272101962 | 03 314 7233 | amberley.dispensary@gmail.com | pvwatt@slingshot.co.nz | 2 | 0 | 0 | 0 | 2 | 2 | 4 | 17/11. Quieter than usual. | 16/11. Fully operational, less business than usual.
Rural 2 | Surgery | Amuri Community Health Centre | 40 Wilkin Street Rotherham | 03 315 6328 | Scrivener, Graeme | Doctor | 0211801790 | 03 315 7109 | drscrivener@amurihc.co.nz |  | 6 | 0 | 4 | 2 | 0 | 6 | 6 | 17/11. Fully operational. Adequate staff; cell, email and internet functioning. | 16/11. Comms Centre being set up in Waiau today? Internet restored except access to ERMS, HealthOne. | Waiau community of concern.
Rural 2 | Surgery | Cheviot Community Health Centre | 6 Robinson Street Cheviot | 03 319 8630 | Hill, Donna | Administration | 0276026621 |  | admin@cchc.co.nz | cchc@xtra.co.nz | 6 | 0 | 4 | 2 | 0 | 8 | 8 | 17/11. No additional information. | 16/11. RCPHO sent locum GP to practice Wed to Friday; more GPs on standby.
| Pharmacy | Cheviot Pharmacy Depot | [8 empty] | 2 | 0 | 0 | 0 | 2 | 6 | 8 | 17/11. IT back on line. | 16/11. Services on, BAU but slower than usual.
Rural 2 | Surgery | Hanmer Springs Health Centre | 59 Jacks Pass Rd Hanmer Springs | 03 315 7503 | Smith, David | Administration | 0274311212 |  | manager@hanmermc.co.nz |  | 4 | 0 | 2 | 0 | 2 | 4 | 4 | 17/11. No additional information. | 16/11. Seeing stressed/anxious patients, extended consults. Also carrying extraordinary costs related to quake (on call requirements). Keeping a log. | Additional mental health resources required - RCPHO will organise. Additional extended mh consult funding required.
| Pharmacy | Hanmer Pharmacy Depot | [8 empty] | 2 | 0 | 0 | 0 | 2 | 6 | 8 | 17/11. Still no internet, no EFTPOS. | 16/11. Services on, BAU but slower than usual.
Rural 1 | Surgery | Kaikoura Healthcare | 25 Deal Street Kaikoura | 03 319 3500 | Judd, Andrea | Doctor | 0276863636 | 03 319 6480 | andreaj@kaikourahc.co.nz | judd.harnett@xtra.co.nz | 8 | 0 | 2 | 4 | 2 |  | 12 | 17/11. GP covered. Next week ok for GP cover (need 5 to operate). New relief nurses/GPs coming in soon. PHN asking for assistance. Gastro 1st case in today. Still need receptionist cover. May need practice manager relief - TBC. CDHB Vuln People team flying up . tomorrow; more coming next week. 4WDs need permit from Hurunui DC. Army and Police manning roadblock. Must have 4WD to access road. Telephones intermittent - use cell phones to contact. | 16/11. 16/11. Locum GP and nurse relief required. Travel and accommodation will be required. Simon Brokenshire (24HS) coordinating GP/PN relief. | Mental health supports - being organised by CDHB Vuln People team. Will need reception relief next week.
Rural 1 | Pharmacy | Kaikoura Pharmacy | 37 West End Kaikoura | 03 319 5035 | McKee, Dave | Pharmacist and Other | 0275694174 | 03 319 7067 | david@kaikourapharmacy.co.nz | kaikoura.pharmacy@xtra.co.nz | 16 | 4 | 4 | 4 | 4 | 14 | 14 | 17/11. Still no water, relief pharmacist supposed to arrive this morning but delayed by weather, pharmaceutical order arrived yesterday, further pharmacist support required. Dispensing very very high volumes. Require further pharmacist transport Friday AM | 16/11. Operating 10-4 from usual premises. Pharmaceuticals being helicoptered in at 10am today. Has 2 weeks' supply. Reduced support from usual pharmacy technician. Transport and accommodation required for locum pharmacist. | Transportation and accommodation of 2 locum pharmacists
Rural 2 | Surgery | Waikari Health Centre | 100 Princes Street Waikari | 03 314 4506 | Allan, Wendy | Administration | 0274652540 | 03 314 3887 | admin@waikarihealth.co.nz |  | 2 | 0 | 2 | 0 | 0 | 2 | 2 | 17/11. No additional information. | 16/11. BAU.
n/a | CD | Woodend Community Centre | [16 empty] | Mental Health Team Leader was at centre 15 Nov. Low volume but high value activity.
n/a | CD | Hurunui Community Centre
PERIPHERAL PRACTICES AND PHARMACIES
Rural 3 | Surgery | Durham Health (Rangiora) | 15 Durham Street Rangiora | 03 313 4659 | Cable, Sue | Administration | 0273648520 |  | sue@durhamhealth.co.nz |  | 2 | 0 | 0 | 2 | 0
Rural 3 | Surgery | Good Street Medical Centre (Rangiora) | 17 Good Street Rangiora | 03 313 8262 | Henley, Jo | Administration | 0272595900 | 03 312 8566 | receptionist@gsmc.co.nz |  | 0
Rural 3 | Surgery | Medical Corner Doctors (Rangiora) | 237 High Street Rangiora | 03 313 7877 | Tapper, Nigel | Doctor | 0276316296 | 03 313 7819 | ntapper@gmail.com |  | 0
Rural 3 |  |  |  |  | Pickles, Rachael | Administration | 0226825655 |  | practicemanager@medicalcorner.co.nz |  | 0
Rural 3 | Surgery | Pegasus Medical Centre | 52 Pegasus Main Street Pegasus | 03 920 4060 | Robinson, Janet | Doctor | 021432805 | 03 314 8564 | janetrobinson@clear.net.nz |  | 0
Rural 3 | Surgery | Rangiora Family Doctors | 36 Victoria Street Rangiora | 03 313 7197 | Scragg, Alf | Doctor | 02102361031 | 03 312 0028 | alf.scragg@rnzcgp.org.nz |  | 0
Rural 3 | Surgery | Southside Health (Rangiora) | 10F Newnham Street Rangiora | 03 313 5252 | Rogers, Bevan | Doctor | 0274571707 | 03 312 8151 | bevan@southsidehealth.co.nz | bevan@jazzbears.co.nz | 0
Rural 3 | Surgery | Woodend Medical Centre | 51 Main Road Woodend | 03 312 7333 | McGregor, Steve | Doctor | 0272285637 | 03 351 2044 | info@woodendmedical.co.nz |  | 0
Rural 3 | Pharmacy | Life Pharmacy Rangiora | 174 High Street Rangiora | 03 313 6340 | Smith, Graeme | Pharmacist | 02102266523 | 03 313 9573 | pharmacy@liferangiora.co.nz | graemes05@yahoo.co.nz | 0 | [7 empty] | Rangiora/Kaiapoi pharmacies fully operational
Rural 3 | Pharmacy | Pegasus Pharmacy | 52, Pegasus Main Street Pegasus | 03 920 4081 | Watt, Nicky | Pharmacist | 021756608 | 03 314 7233 | pegasus.dispensary@gmail.com | pvwatt@slingshot.co.nz | 0
Rural 3 | Pharmacy | Rangiora Pharmacy | 120 High Street Rangiora | 03 313 6366 | Knight, Greg | Pharmacist | 0276403245 | 03 343 1109 | greg@rangiorapharmacy.co.nz | greg.k@slingshot.co.nz | 0
Rural 3 | Pharmacy | Stans 7 Day Pharmacy (Rangiora) | 15 Ashley Street Rangiora | 03 313 8280 | Ho, Eddie | Pharmacist | 0211895752 |  | mcintoshpharmacychch@gmail.com | kcho007@gmail.com | 0
Rural 3 | Pharmacy | Unichem Medical Corner Pharmacy (Rangiora) | 237a High Street Rangiora | 03 313 8624 | Sinclair, Stephanie | Pharmacist | 0273293956 | 03 312 6430 | stephanie@umcpharmacy.co.nz | sinclairs78@yahoo.co.nz | 0
Rural 4 | Surgery | Oxford Community Health Centre | 39 Park Ave Oxford | 03 312 4195 | Woodham, Chantal | Administration | 021407440 | 03 312 5313 | chantal@ochc.co.nz | admin@ochc.co.nz | 0
Rural 4 | Pharmacy | Oxford Pharmacy | 49b Main Street Oxford | 03 312 4314 | Miller, Tracie | Pharmacist | 021855009 | 03 312 0287 | tracie@oxpharm.co.nz | tracieracie@hotmail.com | 0
Rural 5 | Surgery | Kaiapoi Family Doctors | 42 Charles Street Kaiapoi | 03 327 7474 | Fairhall, Gerard | Doctor | 0274310178 |  | gcfairhall@xtra.co.nz | admin@kfd.co.nz | 0
Rural 5 | Surgery | Kaiapoi Medical Centre | 69 Fuller Street Kaiapoi | 03 327 5115 | Crighton, Ros | Other | 021796317 | 03 327 6788 | pm@kmcemail.co.nz | ros.crighton@gmail.com | 0
Rural 5 | Surgery | Kaiapoi-Kaye Buchan Medical Centre | 164 Williams Street Kaiapoi | 03 327 2622 | Buchan, Kaye | Doctor | 0272792466 | 03 355 2466 | kbuchanreception@xtra.co.nz | kbuchan@xtra.co.nz | 0
Rural 5 | Pharmacy | Kaiapoi Crossing Pharmacy | 77 Hilton Street Kaiapoi | 03 327 8077 | Singh, Presant | Pharmacist | 0210487105 |  | kaiapoi@crossingpharmacy.co.nz | presant.singh@gmail.com | 0
Rural 5 | Pharmacy | Kaiapoi North Pharmacy | 40 Charles Street Kaiapoi | 03 327 8069 | Hobill, Peter | Pharmacist | 0272240513 | 03 351 4511 | dispensary@kaiapoipharmacy.co.nz | peter@kaiapoipharmacy.co.nz | 0
Rural 5 | Pharmacy | Unichem Fenwicks Pharmacy (Kaiapoi) | 129 Williams St Kaiapoi | 03 327 7339 | Fenwick, Rob | Pharmacist | 0274103531 | 03 352 6736 | fenwick@pharmacy.unichem.co.nz | rfen@xtra.co.nz | 0
Rural 8 | Surgery | Darfield Medical Centre Limited | 159 Horndon Street Darfield | 03 318 8511 | Vlok, Johan | Doctor | 0212949693 |  | drjohanvlok@gmail.com |  | 0
Rural 9 | Surgery | Methven Medical Centre | The Square Methven | 03 302 8105 | O'Duffy, Gayle | Doctor | 0274350981 |  | DrGayle.mmc@methvenmedical.co.nz | oduffy@paradise.net.nz | 0
Rural 9 | Pharmacy | Methven Pharmacy | 101 Main Street Methven | 03 302 8103 | Malkonyan, Atif | Pharmacist | 0211837183 |  | methven.pharmacyltd@gmail.com | protein_us@hotmail.com | 0
Sample INTEL report - It might be useful to track the status of practices over time, so this sheet shows 17 Nov, 16 and 15 Nov.
However, in practice this makes the spreadsheet unwieldy with multiple days.

## 15 Nov
LEG | Type | Surgery/Pharmacy | Address | Business Phone | Emergency Contacts | Role | Cellphone | Homephone | Email1 | Email2 | STATUS | Building | Services | Staff | Income | NOTES | LOGISTIC NEEDS
Rural 2 | Surgery | Amberley Medical Centre | 6 Hilton Drive Amberley | 03 314 8504 | Long, Christine | Nurse | 0274278813 | 03 314 9077 | chrisl@amberleymc.co.nz | long.chris@xtra.co.nz | 2 | 0 | 0 | 0 | 2 | 15/11. fully operational, business slow
Rural 2 | Pharmacy | Amberley Pharmacy | 127a Carters Rd Amberley | 03 314 8211 | Watt, Paul | Pharmacist | 0272101962 | 03 314 7233 | amberley.dispensary@gmail.com | pvwatt@slingshot.co.nz | 4 | 0 | 2 | 0 | 2 | 15/11. fully operational, business slow, couriers operating
Rural 2 | Surgery | Amuri Community Health Centre | 40 Wilkin Street Rotherham | 03 315 6328 | Scrivener, Graeme | Doctor | 0211801790 | 03 315 7109 | drscrivener@amurihc.co.nz |  | 6 | 0 | 4 | 2 | 0 | 15/11. no telecomms. Landline taken out by slip. Power, water, sewer ok. Generator backup ready. Pts have to show up to be seen - no way to ring for appt. 2 docs working today; no staffing issues.
Rural 2 | Surgery | Cheviot Community Health Centre | 6 Robinson Street Cheviot | 03 319 8630 | Hill, Donna | Administration | 0276026621 |  | admin@cchc.co.nz | cchc@xtra.co.nz | 8 | 0 | 4 | 4 | 0 | 15/11. GP personal issues. RCPHO sent locum GP to practice 14/11; more GPs on standby.
| Pharmacy | Cheviot Pharmacy Depot | [8 empty] | 8 | 0 | 4 | 0 | 4 | 15/11. All services back on.
Rural 2 | Surgery | Hanmer Springs Health Centre | 59 Jacks Pass Rd Hanmer Springs | 03 315 7503 | Smith, David | Administration | 0274311212 |  | manager@hanmermc.co.nz |  | 4 | 0 | 2 | 0 | 2 | 15/11. Bridge open. BAU. Power, sewer, water on. couriers operating, increased anxiety presenting
| Pharmacy | Hanmer Pharmacy Depot | [8 empty] | 8 | 0 | 4 | 0 | 4 | 15/11. All services back on. Some EFTPOS issues.
Rural 1 | Surgery | Kaikoura Healthcare | 25 Deal Street Kaikoura | 03 319 3500 | Judd, Andrea | Doctor | 0276863636 | 03 319 6480 | andreaj@kaikourahc.co.nz | judd.harnett@xtra.co.nz | 12 | 2 | 4 | 4 | 2 | 15/11. no telecomm, power, sewer. On generator power. New bldg, minor issues. NEED TO CONFIRM POWER. | 1. Portapotty. 2. Fuel for generator (CDHB already onto this?).
Rural 1 | Pharmacy | Kaikoura Pharmacy | 37 West End Kaikoura | 03 319 5035 | McKee, Dave | Pharmacist and Other | 0275694174 | 03 319 7067 | david@kaikourapharmacy.co.nz | kaikoura.pharmacy@xtra.co.nz | 14 | 2 | 4 | 4 | 4 | 15/11. CP working as dispensary from health ctr. Power ok. No water, sewer. Telecomms intermittent. Cannot charge $. Worried about reimb. Thinks will be back in shop 16/11. | 1. Need to confirm emergency supplies funding. 2. Concerned re safety re drug seekers. 3. Would like locum CP. 4. Needs stock to be delivered from wholesaler in CHCH. 5. Portapotty
Rural 2 | Surgery | Waikari Health Centre | 100 Princes Street Waikari | 03 314 4506 | Allan, Wendy | Administration | 0274652540 | 03 314 3887 | admin@waikarihealth.co.nz |  | 2 | 0 | 2 | 0 | 0 | 15/11. Fully operational. Business slow. Patients presenting with anxiety.
| CD | Woodend Community Centre | [13 empty] | 14/11. GP locum are available if req'd. Expecting 100 tourists to be helicoptered out. 15/11. no contact
| CD | Hurunui Community Centre | [13 empty] | 15/11. no contact, although Civil Def would like 24/7 mental health support. PHO has offered 0800 and LanguageLine.
PERIPHERAL PRACTICES AND PHARMACIES
Rural 3 | Surgery | Durham Health (Rangiora) | 15 Durham Street Rangiora | 03 313 4659 | Cable, Sue | Administration | 0273648520 |  | sue@durhamhealth.co.nz |  | 2 | 0 | 0 | 2 | 0 | Rangiora/Kaiapoi practices fully operational. seeing increased patients w/ stress/anxiety. RCPHO sending BIC workers to support. | ?BIC/mh resources
Rural 3 | Surgery | Good Street Medical Centre (Rangiora) | 17 Good Street Rangiora | 03 313 8262 | Henley, Jo | Administration | 0272595900 | 03 312 8566 | receptionist@gsmc.co.nz |  | 0
Rural 3 | Surgery | Medical Corner Doctors (Rangiora) | 237 High Street Rangiora | 03 313 7877 | Tapper, Nigel | Doctor | 0276316296 | 03 313 7819 | ntapper@gmail.com |  | 0
Rural 3 |  |  |  |  | Pickles, Rachael | Administration | 0226825655 |  | practicemanager@medicalcorner.co.nz |  | 0
Rural 3 | Surgery | Pegasus Medical Centre | 52 Pegasus Main Street Pegasus | 03 920 4060 | Robinson, Janet | Doctor | 021432805 | 03 314 8564 | janetrobinson@clear.net.nz |  | 0
Rural 3 | Surgery | Rangiora Family Doctors | 36 Victoria Street Rangiora | 03 313 7197 | Scragg, Alf | Doctor | 02102361031 | 03 312 0028 | alf.scragg@rnzcgp.org.nz |  | 0
Rural 3 | Surgery | Southside Health (Rangiora) | 10F Newnham Street Rangiora | 03 313 5252 | Rogers, Bevan | Doctor | 0274571707 | 03 312 8151 | bevan@southsidehealth.co.nz | bevan@jazzbears.co.nz | 0
Rural 3 | Surgery | Woodend Medical Centre | 51 Main Road Woodend | 03 312 7333 | McGregor, Steve | Doctor | 0272285637 | 03 351 2044 | info@woodendmedical.co.nz |  | 0
Rural 3 | Pharmacy | Life Pharmacy Rangiora | 174 High Street Rangiora | 03 313 6340 | Smith, Graeme | Pharmacist | 02102266523 | 03 313 9573 | pharmacy@liferangiora.co.nz | graemes05@yahoo.co.nz | 0 |  |  |  |  | Rangiora/Kaiapoi pharmacies fully operational
Rural 3 | Pharmacy | Pegasus Pharmacy | 52, Pegasus Main Street Pegasus | 03 920 4081 | Watt, Nicky | Pharmacist | 021756608 | 03 314 7233 | pegasus.dispensary@gmail.com | pvwatt@slingshot.co.nz | 0
Rural 3 | Pharmacy | Rangiora Pharmacy | 120 High Street Rangiora | 03 313 6366 | Knight, Greg | Pharmacist | 0276403245 | 03 343 1109 | greg@rangiorapharmacy.co.nz | greg.k@slingshot.co.nz | 0
Rural 3 | Pharmacy | Stans 7 Day Pharmacy (Rangiora) | 15 Ashley Street Rangiora | 03 313 8280 | Ho, Eddie | Pharmacist | 0211895752 |  | mcintoshpharmacychch@gmail.com | kcho007@gmail.com | 0
Rural 3 | Pharmacy | Unichem Medical Corner Pharmacy (Rangiora) | 237a High Street Rangiora | 03 313 8624 | Sinclair, Stephanie | Pharmacist | 0273293956 | 03 312 6430 | stephanie@umcpharmacy.co.nz | sinclairs78@yahoo.co.nz | 0
Rural 4 | Surgery | Oxford Community Health Centre | 39 Park Ave Oxford | 03 312 4195 | Woodham, Chantal | Administration | 021407440 | 03 312 5313 | chantal@ochc.co.nz | admin@ochc.co.nz | 0
Rural 4 | Pharmacy | Oxford Pharmacy | 49b Main Street Oxford | 03 312 4314 | Miller, Tracie | Pharmacist | 021855009 | 03 312 0287 | tracie@oxpharm.co.nz | tracieracie@hotmail.com | 0
Rural 5 | Surgery | Kaiapoi Family Doctors | 42 Charles Street Kaiapoi | 03 327 7474 | Fairhall, Gerard | Doctor | 0274310178 |  | gcfairhall@xtra.co.nz | admin@kfd.co.nz | 0
Rural 5 | Surgery | Kaiapoi Medical Centre | 69 Fuller Street Kaiapoi | 03 327 5115 | Crighton, Ros | Other | 021796317 | 03 327 6788 | pm@kmcemail.co.nz | ros.crighton@gmail.com | 0
Rural 5 | Surgery | Kaiapoi-Kaye Buchan Medical Centre | 164 Williams Street Kaiapoi | 03 327 2622 | Buchan, Kaye | Doctor | 0272792466 | 03 355 2466 | kbuchanreception@xtra.co.nz | kbuchan@xtra.co.nz | 0
Rural 5 | Pharmacy | Kaiapoi Crossing Pharmacy | 77 Hilton Street Kaiapoi | 03 327 8077 | Singh, Presant | Pharmacist | 0210487105 |  | kaiapoi@crossingpharmacy.co.nz | presant.singh@gmail.com | 0
Rural 5 | Pharmacy | Kaiapoi North Pharmacy | 40 Charles Street Kaiapoi | 03 327 8069 | Hobill, Peter | Pharmacist | 0272240513 | 03 351 4511 | dispensary@kaiapoipharmacy.co.nz | peter@kaiapoipharmacy.co.nz | 0
Rural 5 | Pharmacy | Unichem Fenwicks Pharmacy (Kaiapoi) | 129 Williams St Kaiapoi | 03 327 7339 | Fenwick, Rob | Pharmacist | 0274103531 | 03 352 6736 | fenwick@pharmacy.unichem.co.nz | rfen@xtra.co.nz | 0
Rural 8 | Surgery | Darfield Medical Centre Limited | 159 Horndon Street Darfield | 03 318 8511 | Vlok, Johan | Doctor | 0212949693 |  | drjohanvlok@gmail.com |  | 0
Rural 9 | Surgery | Methven Medical Centre | The Square Methven | 03 302 8105 | O'Duffy, Gayle | Doctor | 0274350981 |  | DrGayle.mmc@methvenmedical.co.nz | oduffy@paradise.net.nz | 0
Rural 9 | Pharmacy | Methven Pharmacy | 101 Main Street Methven | 03 302 8103 | Malkonyan, Atif | Pharmacist | 0211837183 |  | methven.pharmacyltd@gmail.com | protein_us@hotmail.com | 0
Sample early INTEL report - this info feeds into SITREP which is distributed widely. SITREP does not need the numbers, just the colour coding.
Colour coding is based on the Practice & Pharmacy Status Definition algorithm document.